## Project Dashboard
PROJECT PORTFOLIO DASHBOARD
Updated: 2026-01-03 17:01
TOTAL PROJECTS |  |  | ON TRACK |  |  | AT RISK | DELAYED
15 |  |  | 10 |  |  | 3 | 2
PORTFOLIO METRICS
Overall Completion | 68% | Progress
Budget Utilization | 78% | Spending
Resource Capacity | 85% | Allocation
Schedule Performance | 92% | On-time
PROJECT STATUS SUMMARY
Project | Manager | Start | End | Progress | Budget | Status
Website Redesign | Alice | 2024-01-15 | 2024-06-30 | 85% | 125000 | On Track
Mobile App v2 | Bob | 2024-02-01 | 2024-08-15 | 60% | 250000 | At Risk
CRM Integration | Carol | 2024-03-01 | 2024-07-31 | 45% | 85000 | On Track
Data Migration | David | 2024-01-01 | 2024-04-30 | 100% | 175000 | Complete
API Gateway | Eve | 2024-04-01 | 2024-09-30 | 25% | 95000 | Delayed

## Task Tracker
TASK MANAGEMENT TRACKER
Task ID | Task Name | Assigned To | Start Date | End Date | Duration | Status | % Complete | Priority
T-001 | Requirements Gathering | Alice | 2024-06-01 | 2024-06-08 |  | Complete | 100% | High
T-002 | System Design | Bob | 2024-06-06 | 2024-06-18 |  | Complete | 100% | High
T-003 | Database Schema | Carol | 2024-06-11 | 2024-06-16 |  | Complete | 100% | High
T-004 | API Development | David | 2024-06-13 | 2024-06-28 |  | In Progress | 75% | High
T-005 | Frontend Framework | Eve | 2024-06-16 | 2024-06-26 |  | In Progress | 60% | Medium
T-006 | User Authentication | Alice | 2024-06-21 | 2024-06-29 |  | In Progress | 40% | High
T-007 | Payment Integration | Bob | 2024-06-26 | 2024-07-08 |  | Not Started | 0% | High
T-008 | Email Notifications | Carol | 2024-06-29 | 2024-07-04 |  | Not Started | 0% | Medium
T-009 | Admin Dashboard | David | 2024-07-01 | 2024-07-11 |  | Not Started | 0% | Medium
T-010 | Testing Phase 1 | Eve | 2024-07-06 | 2024-07-13 |  | Not Started | 0% | High
T-011 | Bug Fixes Round 1 | Alice | 2024-07-11 | 2024-07-16 |  | Not Started | 0% | High
T-012 | Performance Optimization | Bob | 2024-07-13 | 2024-07-21 |  | Not Started | 0% | Medium
T-013 | Security Audit | Carol | 2024-07-16 | 2024-07-21 |  | Not Started | 0% | High
T-014 | Documentation | David | 2024-07-19 | 2024-07-26 |  | Blocked | 10% | Low
T-015 | Deployment | Eve | 2024-07-23 | 2024-07-26 |  | Not Started | 0% | High

## Resource Matrix
RESOURCE ALLOCATION MATRIX
Hours allocated per team member per project
Team Member | Project A | Project B | Project C | Project D | Project E | Total Hours | Utilization %
Alice Chen | 40 | 32 | 24 | 16 | 8
Bob Smith | 24 | 48 | 16 | 32 | 0
Carol Davis | 16 | 24 | 48 | 8 | 24
David Lee | 32 | 16 | 8 | 40 | 24
Eve Wilson | 8 | 0 | 32 | 24 | 56
Frank Brown | 24 | 40 | 0 | 16 | 40
Grace Kim | 16 | 8 | 24 | 48 | 24
Henry Zhang | 0 | 32 | 40 | 8 | 40
Project Total

## Risk Register
PROJECT RISK REGISTER
Risk ID | Description | Category | Probability | Impact | Risk Score | Mitigation | Owner | Status
R-001 | Key developer leaves project | Resource | 3 | 5 |  | Backup training program | HR Manager | Open
R-002 | Third-party API changes | Technical | 4 | 4 |  | Abstract API layer | Tech Lead | Mitigating
R-003 | Budget overrun by 20% | Budget | 2 | 4 |  | Monthly budget reviews | PM | Open
R-004 | Requirements scope creep | Schedule | 4 | 3 |  | Change control process | PM | Mitigating
R-005 | Security vulnerability found | Technical | 3 | 5 |  | Security audits | Security Lead | Open
R-006 | Integration delays | Schedule | 3 | 3 |  | Parallel development | Tech Lead | Closed
R-007 | Data migration issues | Technical | 4 | 4 |  | Rollback procedure | DBA | Accepted
R-008 | Vendor contract renewal | External | 2 | 3 |  | Early negotiation | Procurement | Open
R-009 | Performance bottleneck | Technical | 3 | 4 |  | Load testing | QA Lead | Mitigating
R-010 | Regulatory compliance change | External | 2 | 5 |  | Legal monitoring | Compliance | Open
RISK SUMMARY
High Risk (13-25)
Medium Risk (6-12)
Low Risk (1-5)
Total Risks

## Milestone Timeline
PROJECT MILESTONE TIMELINE
Milestone | Planned Date | Actual Date | Days Variance | Status | Notes
Project Kickoff | 2024-01-15 | 2024-01-15 |  |  | Completed on schedule
Requirements Signed Off | 2024-02-01 | 2024-01-30 |  |  | Completed early
Design Review | 2024-02-28 | 2024-03-05 |  |  | Minor delay due to revisions
Development Phase 1 | 2024-04-15 | 2024-04-12 |  |  | Completed ahead of schedule
Integration Testing | 2024-05-30 | 2024-06-03 |  |  | Extended testing needed
User Acceptance Testing | 2024-06-30 | 2024-06-28 |  |  | Minor issues resolved
Security Audit | 2024-07-15 | - | - |  | Scheduled
Performance Testing | 2024-07-30 | - | - |  | Scheduled
Go-Live Preparation | 2024-08-15 | - | - |  | Pending
Production Deployment | 2024-08-30 | - | - |  | Pending
Post-Launch Support | 2024-09-15 | - | - |  | Planned
Project Closure | 2024-09-30 | - | - |  | Planned
TIMELINE ANALYSIS
Today's Date
Milestones Completed
Average Variance (days)
Max Delay (days)